## Slide 1: Integrating Heart Failure Care
PROJECT CHARTER – (enter name of team)
(Enter Date)

## Slide 2
Prepared by: |  | Date: | 
Role | Name | Title | Signature | Date
Project Manager |  |  |  | 
Clinical Lead(s) |  |  |  | 
Administrative Lead(s) |  |  |  | 
Project Sponsor |  |  |  | 
Executive Sponsor(s) |  |  |  | 
Integrating Heart Failure Care – Project Sponsorship
Approvals
Notes: Approval of the Project Charter signifies understanding, alignment, and commitment to the content described herein. The Project Charter must be approved by the Executive Sponsor, Project Sponsor, and Project Manager before the Definition Phase can be initiated. Project team members/organizational partners also sign-off the charter to confirm their understanding, alignment, and commitment to the work. Once completed & approved, the charter forms the basis for detailed planning and future decision-making.

## Slide 3: Contents
Section 1: Project Overview
  1.1 Project Description
  1.2 Project Purpose
  1.3 Project Goals And Objectives
  1.4 Guiding Principles
  1.5 Project Scope
  1.6 Critical Success Factors
  1.7 Success Criteria
  1.8 Risks
  1.9 Constraints
Section 2: Major Milestones and Cost Estimates
  2.1 Major Milestones
  2.2 Cost Estimates
  2.3 Funding Sources
Section 3: Project Team
  3.1 Project Roles & Responsibilities
  3.2 Project Governance Structure
Section 4: Sign-off
  4.1 Signatures

## Slide 4: Section 1: Project Overview

## Slide 5: 1.1 Project Description
HF is a chronic condition and the dynamic nature of the course of the disease presents challenges in care and control. A growing body of evidence in the form of guidelines, reports and recommendations is suggesting that HF care and control requires a system approach. Specifically, “this system must meet and anticipate the evolving goals and complexity of aging patients throughout their entire journey with HF, providing access to specialized services, community supports, and end-of-life care according to patient needs and preferences” (Can J Cardiology 2017; 33: 1410).
(insert additional information here. See Notes section below for more details)
Notes: Provide a brief description of the project in business terms, outlining the reason(s) for initiating the project. Focusing on relevant facts, provide necessary background to understand why the project was started, what problem it will solve, what value it will have. Lay out the narrative so someone who is not familiar with the project can reference this section, and understand what the project aims to achieve and why – be brief, clear, and explicit in the description.
Summarize key aspects of the project by answering the following questions:
How and why was the project initiated?
Who will use the final deliverable/output?
Who will be affected by this work? (both internal/external perspectives)
What are the missed opportunities of not doing this work?
What are the business challenges if this work is not done?
Etc.

## Slide 6: 1.2 Project Purpose
Implementation of a Spoke-Hub-Node Model of integrated heart failure care and a heart failure care Quality Standard in (enter region here).
Project aim and intended outcomes focused on integrating care are to:
  Improve compliance with clinical best practices
  Reduce variation in practice and outcomes
  Improve patient experience
  Improve access and care closer to home
  Better integrate care across the patient continuum
  Better resources use and value for money
Notes: Describe the business reason(s) for initiating the project, specifically stating the expected benefits and outcomes of the project. i.e., what problem does this work solve and how will this work solve that problem? Think big picture - WHY are we doing this work; why are we spending our time, why are we investing, or why should we invest in it…what are the outcomes we expect to achieve?

## Slide 7: 1.3 Project Goals And Objectives
Improve integrated HF care for patients living in (enter region here).
Implement the Spoke-Hub-Node model and the HQO heart failure Quality Standard.
Report on the implementation of the Spoke-Hub-Node Model and HQO heart failure Quality Standard, providing an ongoing sustainability/maintenance plan. To include:
  Current State & Gap Analysis
  Implementation Approach
  Qualitative evaluation of successes/lessons learned
  Sustainability/maintenance plan
Goals
Objective(s)
Notes: Provide the details of what this project aims to accomplish by listing its specific goals, objectives, and deliverables. State the goals in terms of high-level outcomes to be achieved; goals are typically intangible or abstract. Identify specific objectives/ deliverables for each goal listed. Objectives are clear statements with concrete measurement criteria. Deliverables are tangible, verifiable outcomes that signify completion of objectives. Include the measurement criteria that will be used to confirm an objective and the outcome have been successfully achieved. Define goals and objectives in SMARTS terms. Effective goals are:
• Specific – we should know exactly what is expected
• Measurable - measurements are established so performance or progress toward meeting goals can be monitored and evaluated
• Achievable - the goal is not just a wish, it has a basis in reality
• Results Focused - the goal is focused on accomplishments and outcomes, not activities
• Time Bound - the goal has a specific deadline or time frame for accomplishment

## Slide 8: 1.4 Guiding Principles
  ‘Patient-First’ Approach: ensure reflecting the care needs of patients; focus on defined population.
  Equitable: ensure patient accessibility is maximized; care closer to home.
  Evidence-Based: ensure a strong evidence base and established best practices are used to inform implementation.
  Continued Evaluation: ensure continual evaluation of services, with regular sharing of success/failures and associated learnings; continuous care improvement.
  Interdisciplinary & Clinician Integration: encourage standardized care delivery through interprofessional teams; organizational support and commitment. Engage clinicians in a leading role, with vision to instill a strong, cohesive culture.
  Comprehensive services across the care continuum: foster cooperation across and between organizations; access to care continuum with multiple points of access.
  Information Systems: ensure the use of information systems to collect, track and report activities; enhance communication and information flow across the continuum of care.
Notes: The above are examples to get you started. Revise as needed to reflect the priorities and values of your group.

## Slide 9: 1.5 Project Scope
IN SCOPE Specific items that WILL be included as part of the work performed by this project.
Facilitated implementation of Spoke-Hub-Node model and HQO Heart Failure Quality Standard
Design: establish leadership table & work plan
Develop: complete current state, gap analysis and future state
Implement: begin adoption of best-practice standards (i.e., Implementation Approach)
Evaluate: qualitative assessment of successes and lessons learned
Coordination and management of Integrated Heart Failure initiative in (enter name of region)
Ensuring that clinical and administrative leadership are kept informed of major project activities
Maintain regular communication and report back to the necessary groups and individuals on ongoing project activities
This section describes work on products or services that are outside the boundaries of the project, that have the potential to derail or detract group efforts from project objectives.
OUT of SCOPE Specific items that WILL NOT be included as part of the work performed by this project.
Notes: The project scope describes the work that must be done to complete the project; it defines project limits and identifies the products and/or services delivered by the project. The scope statement should also describe products and/or services that are outside of the boundaries of the project. This information serves as the basis for making future project decisions and for managing expectations among stakeholders.

## Slide 10: 1.6 Critical Success Factors
Dedicated local clinical and administrative leadership.
Availability of local resource for managing/coordinating project.
Identification and allocation of resources (time, people) to project activities.
Regular team/leadership table meetings and communication of updates on key project work streams.
Effective and timely communications to respective governance leadership of major project activities, and communications to all stakeholders.
Notes: Describe the factors or characteristics that are deemed critical to the success of the project, such that, in their absence the project will fail. Include significant events or decisions that need to take place. Whenever possible, ensure factors are specific and measurable.

## Slide 11: 1.7 Success Criteria
Successful implementation of the Spoke-Hub-Node Model and HQO Quality Standard.
Notes: Describe the explicit and measurable criteria that will be used at the end of the project to determine whether or not the project has been successful.

## Slide 12: 1.8 Risks
No. | Risk Description List high-level risk events that pose threats or opportunities to the project. | Probability (H/M/L) | Impact (H/M/L) | Planned Mitigation Explain what will be done to avoid, transfer, mitigate or accept risks listed.
1. |  |  |  | 
2. |  |  |  | 
3. |  |  |  | 
Notes: Consider ‘what if’… Document high-level project risks apparent at this point that could negatively impact the achievement of project goals and objectives. Indicate initial probability and impact. Focus on risks that are likely to happen and have significant effect on project success. Be sure to consider risks associated with people & organization change and adoption, communication, knowledge translation and exchange, technology, resources, scope, budget, quality, schedules, transition to operations, etc.

## Slide 13: 1.9 Constraints
No. | Category | Constraints Consider time, budget, scope, quality, technology, availability/skills of resources, priorities, approvals, legislation, etc.
 | Time | 
 | Budget | 
 | Resources | 
 | Other Priorities | 
Notes: Constraints are factors outside the control of the project team, which restrict or regulate the project. They limit available options and affect performance of the project.
Describe the specific project constraints or restrictions being imposed in areas such as schedule, budget, resources, technology, procurement, purchases, and/or dependencies to other key initiatives products e.g., a hard deadline, a predetermined budget, a set milestone, contract provisions, privacy or security considerations/legislation, technology upgrades, procurement policies and processes, etc. It will help to categorize the constraints if there are several.

## Slide 14: Section 2: Major Milestones and Cost Estimates

## Slide 15: 2.1 Major Milestones & Overall Timeline
Insert key milestone events and dates, or create a timeline.

## Slide 16: 2.2 Cost Estimates
Cost Category | Description | Approximate Cost
One-Time Project Costs |  | 
Total One-time Project Costs |  | 
On-going Operating Costs |  | 
Total Ongoing Operating Costs |  | 
Notes: Identify costs to complete the project. Provide a preliminary estimate of the project’s budget by listing key expense categories and providing approximate costs. Indicate the fiscal years during which these costs will be incurred. Adjust budget categories to match the needs of your project. For input, refer to the items listed in the ABP and Business Case. Include one-time as well as ongoing costs.

## Slide 17: 2.3 Resource Needs
Notes: Identify the resource needs for this project.

## Slide 18: Section 3: Project Team

## Slide 19: 3.1 Project Roles and Responsibilities
Identification of members involved across leadership team, clinical champions (MDs/NP/RN/Allied Health, etc), project management/coordination, key stakeholders, administrative leadership, sub-working groups, etc. and their roles.

## Slide 20: 3.2 Project Governance Structure
Illustrate the project governance structure, outlining the advisory and decision making pathway. Identify the Executive Sponsor, Project Sponsor, Project Manager, project work streams and leads, and any advisory committees (e.g. Patient and Caregiver Advisors).

## Slide 21: Section 4: Sign-off
Notes: List names of project team members and applicable organizational partners. By signing the charter, team members and organizational partners confirm they have understood their roles & responsibilities (or team member’s roles & responsibilities) on this project, and are committed to its successful completion.

## Slide 22: 4.1 Signatures
Role | Name | Title | Signature | Date
Project Manager |  |  |  | 
Clinical Lead(s) |  |  |  | 
Administrative Lead(s) |  |  |  | 
Other Team Members |  |  |  | 
Other Team Members |  |  |  | 
By signing below, you are confirming your understanding, alignment and commitment to the work.
Notes: Approval of the Project Charter signifies understanding, alignment, and commitment to the content described herein. The Project Charter must be approved by the Executive Sponsor, Project Sponsor, and Project Manager. Project team members/organizational partners also sign-off the charter to confirm their understanding, alignment, and commitment to the work. Once completed & approved, the charter forms the basis for detailed planning and future decision-making. It cannot be modified without a formal Project Change Request.